## Defects
Defect # | Status | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
1 | Open | Shehab Badran | V1 | RG02 | 1- Go to " Register user " Page 2- Enter InValid name field 3- press Submit | The System dosen't accept the name field | System Accepts the name | Medium | Medium
2 | Open | Shehab Badran | V1 | RG06 | 1- Go to " Register user " Page 2- Enter InValid Pass field 3- press Submit | The System dosen't accept the Pass field | System Accepts the PASS | Medium | Medium
3 | Open | Shehab Badran | V1 | RG12 | 1- Go to " Register user " Page 2- Enter inValid name field 3- press Submit | System doesn't accept the comapny field | System Accepts the Company | Medium | Medium
4 | Open | Shehab Badran | V1 | RG14 | 1- Go to " Register user " Page 2- Enter inValid name field 3- press Submit | System doesn't accept the Adress field | System Accepts the Adress | Medium | Medium
5 | Open | Shehab Badran | V1 | RG22 | 1- Go to " Register user " Page 2- Enter Invalid mobile no field 10- press Submit | System doesn't accept the Mobile no field | System accept the no field | Medium | Medium
6 | Open | Shehab Badran | V1 | LOG06 | 1-Log in with valid credentials 2-Keep the session idle for 15 minutes. 3-Try to perform an action | A message should be displayed: "Your session has expired. Please log in again." | System Displays Error Message"Confirm Form Resubmission This webpage requires data that you entered earlier in order to be properly displayed. You can send this data again, but by doing so you will repeat any action this page previously performed. Press the reload button to resubmit the data needed to load the page. ERR_CACHE_MISS" | Medium | Medium
7 | Open | Shehab Badran | V1 | PO10 | 1. Navigate to "Order History". 2. Select a shipped order. 3. Click "Cancel Order". | System should display an error: "Order cannot be canceled as it is already shipped." | The system cancels the order | Medium | Medium
8 | Open | Shehab Badran | V1 | PO11 | 1. Navigate to "Order History". 2. Select a shipped order. 3. Click "Cancel Order". | System should display an error: "Order cannot be canceled after delivery." | The system cancels the order | Medium | Medium
9 | Open | Shehab Badran | V1 | CN03 | 1. Navigate to "Contact Us". 2. Enter invalid email format. 3. Fill other fields. 4. Click "Submit" | System should display an error: "Please enter a valid email address." | System displays "The Message has been sent | Medium | Medium
10 | Open | Shehab Badran | V1 | CN04 | 1. Navigate to "Contact Us". 2. Enter a message exceeding the allowed character limit. 3. Click "Submit". | System should display an error: "Message is too long. Please shorten it." | System displays "The Message has been sent | Medium | Medium
11 | Open | Shehab Badran | V1 | CN07 | 1. Navigate to the Newsletter Subscription section. 2. Enter an already subscribed email. 3. Click "Subscribe". | System should display: "You are already subscribed to the newsletter." | System Displays"You have been successfully subscribed!" | Medium | Medium
12 | Open | Shahd Wael Hassan | V1 | CC02 | 1. Go to cart page 2. Increase product quantity 3. Decrease product quantity 4. Verify the correct quantity is displayed | Quantity updates correctly without errors | System Dont allows me to increare or decrease quantity | Medium | Medium
13 | Open | Shahd Wael Hassan | V1 | CC04 | 1. Add a product to the cart 2. Proceed to checkout without logging in 3. Enter shipping details 4. Complete payment process 5. Verify order confirmation | Guest user completes checkout successfully and receives confirmation | System Displays error "Register / Login account to proceed on checkout." | Medium | Medium
14 | Open | Abdelrahman Mahmoud | V1 | PSF_030 | Search using a relevant keyword instead of a product name and observe the results | Related products matching the keyword should be displayed | No results appeared when searching with a keyword. | Medium | Medium